## Reference
Reference data
Transcribed from the site profile, the programme brief and the vendor notice. Blue cells are typed source data; everything on the other sheets computes from here.
Programme week 1 commences | 2026-09-07
Deployment teams | 3
Validation weeks, regulated site | 12
Legacy support ends | 2027-06-30
Support ends, programme week
Code | Site | Country | Users | Master data owned | Depends on | Weeks | Shutdown week | GMP
BRD | Bridgnorth | United Kingdom | 610 | Material master |  | 5 |  | No
HAL | Halesworth | United Kingdom | 240 | Customer master |  | 4 |  | No
KIN | Kinloss | United Kingdom | 180 | Vendor master |  | 4 |  | No
ANT | Antwerp | Belgium | 520 |  | BRD, KIN | 5 |  | No
ROT | Rotterdam | Netherlands | 460 |  | BRD, KIN | 4 |  | No
LYO | Lyon | France | 310 |  | BRD | 4 |  | No
TUR | Turin | Italy | 290 |  | BRD | 4 |  | No
VAL | Valencia | Spain | 205 |  | BRD | 3 |  | No
GDA | Gdansk | Poland | 340 |  | BRD, HAL | 4 |  | No
CHA | Charleston | United States | 580 |  | BRD, HAL | 5 |  | No
MOB | Mobile | United States | 395 |  | BRD, HAL | 4 | 33 | No
SAR | Sarnia | Canada | 260 |  | BRD, HAL | 4 | 24 | No
PEN | Penang | Malaysia | 215 |  | BRD | 3 |  | No
COR | Cork | Ireland | 150 |  | BRD, KIN | 3 |  | Yes
Financial blackout weeks | 3 | 4 | 16 | 17 | 18 | 19 | 20 | 29 | 30 | 42 | 43

## Plan
Verwood Specialty Chemicals ERP cutover sequence
Blue cells are the three planning decisions per site: wave, team and start week. Every other column computes from the Reference sheet.
Wave | Code | Site | Country | Users | Team | Start week | Week commencing | Weeks | End week | Live week | Live date | Binding constraint
1 | BRD |  |  |  | 1 | 5 | [5 empty] | Owns material master; 11 sites depend on it
1 | HAL |  |  |  | 2 | 5 | [5 empty] | Owns customer master; 4 sites depend on it
1 | KIN |  |  |  | 3 | 5 | [5 empty] | Owns vendor master; 3 sites depend on it
2 | CHA |  |  |  | 3 | 10 | [5 empty] | Follows BRD, HAL
2 | COR |  |  |  | 2 | 10 | [5 empty] | Validation runs after cutover, so it must start early despite being the smallest site
3 | ANT |  |  |  | 2 | 21 | [5 empty] | Follows BRD, KIN
3 | ROT |  |  |  | 3 | 21 | [5 empty] | Follows BRD, KIN
4 | SAR |  |  |  | 1 | 24 | [5 empty] | Can only start in its annual shutdown window
4 | GDA |  |  |  | 3 | 25 | [5 empty] | Follows BRD, HAL
5 | LYO |  |  |  | 2 | 31 | [5 empty] | Follows BRD
5 | TUR |  |  |  | 3 | 31 | [5 empty] | Follows BRD
6 | MOB |  |  |  | 1 | 33 | [5 empty] | Can only start in its annual shutdown window
7 | PEN |  |  |  | 2 | 35 | [5 empty] | Follows BRD
7 | VAL |  |  |  | 3 | 35 | [5 empty] | Follows BRD
| TOTAL | [10 empty] | Last go-live across the programme
| Support deadline | [10 empty] | Programme week in which legacy support ends
| Float to the deadline | [10 empty] | Weeks between the last go-live and the end of support

## Timeline
Team loading by programme week
Every cell computes from the Plan sheet. Row 3 flags the financial blackout weeks.
Blackout
Code | 1
Sites live
Team 1
Team 2
Team 3
Peak concurrent |  | Teams available
Cutovers in a blackout week |  | Must be zero

## Checks
Constraint verification
Every result computes from the Plan and Timeline sheets.
Constraint | Test | Result | Detail
Master data, CHA | CHA starts after BRD completes |  | CHA consumes material master owned by BRD
Master data, CHA | CHA starts after HAL completes |  | CHA consumes customer master owned by HAL
Master data, COR | COR starts after BRD completes |  | COR consumes material master owned by BRD
Master data, COR | COR starts after KIN completes |  | COR consumes vendor master owned by KIN
Master data, ANT | ANT starts after BRD completes |  | ANT consumes material master owned by BRD
Master data, ANT | ANT starts after KIN completes |  | ANT consumes vendor master owned by KIN
Master data, ROT | ROT starts after BRD completes |  | ROT consumes material master owned by BRD
Master data, ROT | ROT starts after KIN completes |  | ROT consumes vendor master owned by KIN
Master data, SAR | SAR starts after BRD completes |  | SAR consumes material master owned by BRD
Master data, SAR | SAR starts after HAL completes |  | SAR consumes customer master owned by HAL
Master data, GDA | GDA starts after BRD completes |  | GDA consumes material master owned by BRD
Master data, GDA | GDA starts after HAL completes |  | GDA consumes customer master owned by HAL
Master data, LYO | LYO starts after BRD completes |  | LYO consumes material master owned by BRD
Master data, TUR | TUR starts after BRD completes |  | TUR consumes material master owned by BRD
Master data, MOB | MOB starts after BRD completes |  | MOB consumes material master owned by BRD
Master data, MOB | MOB starts after HAL completes |  | MOB consumes customer master owned by HAL
Master data, PEN | PEN starts after BRD completes |  | PEN consumes material master owned by BRD
Master data, VAL | VAL starts after BRD completes |  | VAL consumes material master owned by BRD
Validation, COR | Live week is the week after cutover plus the validation period |  | The site is not live until validation completes
Shutdown window, SAR | SAR starts in its stated shutdown week |  | Continuous process plant; the turnaround date is fixed a year ahead
Shutdown window, MOB | MOB starts in its stated shutdown week |  | Continuous process plant; the turnaround date is fixed a year ahead
Blackouts, BRD | No blackout week falls inside the cutover
Blackouts, HAL | No blackout week falls inside the cutover
Blackouts, KIN | No blackout week falls inside the cutover
Blackouts, CHA | No blackout week falls inside the cutover
Blackouts, COR | No blackout week falls inside the cutover
Blackouts, ANT | No blackout week falls inside the cutover
Blackouts, ROT | No blackout week falls inside the cutover
Blackouts, SAR | No blackout week falls inside the cutover
Blackouts, GDA | No blackout week falls inside the cutover
Blackouts, LYO | No blackout week falls inside the cutover
Blackouts, TUR | No blackout week falls inside the cutover
Blackouts, MOB | No blackout week falls inside the cutover
Blackouts, PEN | No blackout week falls inside the cutover
Blackouts, VAL | No blackout week falls inside the cutover
Team capacity | No week requires more teams than are available |  | Peak concurrency against the deployment teams available
Deadline | Every site live on or before the support deadline |  | Cork's live date is the end of validation, not the end of cutover
Durations | Team weeks consumed match the site profile |  | No duration has been shortened to make the plan fit
All checks | Count of failures across the tests above |  | Must be zero

## Sequencing
Why the sequence is what it is
The order is set by freedom of movement, not by size
11 of the fourteen sites cannot start until Bridgnorth completes, because Bridgnorth owns material master. Bridgnorth therefore leads regardless of anything else. Halesworth and Kinloss own the other two master domains and run alongside it, so all three teams are committed in wave one and the dependency chain is released in five weeks.
Charleston is the largest site and does not go first
Charleston has 580 users and is the obvious wave one candidate on any size-ordered plan. It depends on both Bridgnorth and Halesworth and cannot start until week 10. Sequencing by size is the error that sank the first internal attempt.
Cork is the smallest site and goes second
Cork has 150 users and would be last on any plan ordered by size or by revenue. It is GMP regulated and needs 12 weeks of computer system validation after the technical cutover before it can transact. Its cutover takes 3 weeks, so it must begin no later than programme week 28 to be live before support ends. Placing it early removes the exposure entirely and costs nothing, because it is small enough to run beside a larger site.
Sarnia and Mobile are fixed points, not choices
Both run continuous plant and can only begin in their annual maintenance shutdown. Sarnia's window is programme week 24 and Mobile's is week 33. The rest of the plan is built around them rather than the reverse, because those dates are set by turnaround contractors and will not move.
The blackouts remove a quarter of the calendar
Eleven of the 43 programme weeks are unavailable: the week containing each quarter end and the week before it, and the first three weeks of January. They fall in clusters, so the usable calendar is four blocks rather than a continuous run. An evenly spread plan lands in them, which is what happened to the second internal attempt.
Where the float is, and what it does not protect
The last go-live is programme week 38 against a deadline of 43, leaving 5 weeks. That float sits at the end of the programme and protects the smallest sites. It does not protect Cork, whose validation is complete long before then, and it does not protect Sarnia or Mobile, whose windows occur once a year.
What would break it
A slip on Bridgnorth moves 11 sites. A slip that causes Sarnia or Mobile to miss its shutdown window moves that site by a full year, which is past the deadline and past the point at which the vendor will answer a support call. Those three sites carry the programme; the rest have room.