CORDELL SPECIALTY COATINGS

Request to Wren & Balfour Environmental Engineering

| From | Anselm Vieira, Plant Manager |
| --- | --- |
| Date | May 11, 2026 |
| Subject | Line 4 project, air permitting |
| Site | Cordell Specialty Coatings, Hollis Junction, Calvert |

We have board approval to install a fourth topcoat line and the equipment order goes in at the end of June. Before it does I need to know what we are walking into on the air permit, because our corporate counsel has told me that if this turns into a major source review the schedule is dead and the project goes back to the board.

My own arithmetic says we are fine. The new line adds about thirty tons a year of solvent after the oxidiser, which is comfortably under the forty ton figure our last consultant told me was the number that matters. I would like that confirmed or corrected before I commit capital.

What I need

Whether the project triggers major source review, and the arithmetic behind it rather than a conclusion.

If it does, what our options are and what each one costs. I would rather spend money on equipment than on offsets and lawyers.

How long each option takes to permit. The line has to be running by the second quarter of next year.

Anything else the project drags in that we have not thought about.

Things you should know

We run Line 4 the same way we run the others, one shift, five days a week, about two hundred and fifty days a year. Nobody here has ever run a coating line around the clock.

We debottlenecked Line 2 last August, mostly a new pump skid and a wider oven. Throughput went up. I do not believe we filed anything for it because nobody told us we had to.

We shut Line 1 down permanently in 2022 and I have always understood we had credit banked from that. If we can use it here, use it.

The oxidiser vendor has quoted the hood arrangement we use on Lines 1 through 3. If a different arrangement helps us, say so, but it has to be in the same building.

- Anselm